## Settings
SETTINGS
Project
| Name of the Project | Team-Builder
Team
| Project Manager | Aaron Yang
| NAME | E-MAIL | PHONE
| Rahil Mehta | rbm5480@psu.edu | 000-000-0000
| Aaron Yang | asy5105@psu.edu | 000-000-0000
000-000-0000
000-000-0000
000-000-0000
000-000-0000
000-000-0000
000-000-0000
000-000-0000
Insert new row above this line

## Project Gantt Chart
Team-Builder
| Today's Date | 2022-11-06 | [12 empty] | © 2022 Spreadsheet123 LTD
| Project Manager | Aaron Yang
| Week Starts from | Monday
| Start Date | 2022-09-18
0
[16 empty] | Sep 2022 | [11 empty] | Oct 2022 | [30 empty] | Nov 2022 | [29 empty] | Dec 2022 | [30 empty] | Jan 2023
WBS | Tasks Name | Assigned to: | Date | Duration | Act. Duration | Complete | Projected End | Actual End | Assigned | Act. Assigned | Complete | Act. Complete | Remaining | Act. Remaining | time axis 2022-09-19 to 2023-01-16
1 | Data Collection | ALL | 2022-09-19 |  | 13 | 100% | 2022-10-01 | 2022-10-01 | 10 | 10 | 0 | 13 | 0 | 0
1.1 | Create survey questions | ... | 2022-09-19 | 3 |  | 100% | 2022-09-21 | 2022-09-21 | 3 | 3 | 3 | 0 | 0 | 0
1.2 | Deploy survey | ... | 2022-09-22 | 7 |  | 100% | 2022-09-28 | 2022-09-30 | 5 | 7 | 7 | 0 | 0 | 0
1.3 | Create github repo | ... | 2022-10-01 | 1 |  | 100% | 2022-10-01 | 2022-09-30 | 0 | -1 | 1 |  | 0
1.4 | Clean and explore data | ... | 2022-09-29 | 2 |  | 100% | 2022-09-30 | 2022-09-30 | 2 | 2 | 2 | 0 | 0 | 0
1.4.1 | Assess and remove any duplicate observations | ... | 2022-09-29 | 1 |  | 100% | 2022-09-29 | 2022-09-30 | 1 | 2 | 1 |  | 0
1.4.2 | Investigate and fix any structural errors (e.g., typos, data inconsistencies, etc.) | ... | 2022-09-29 | 1 |  | 100% | 2022-09-29 | 2022-09-30 | 1 | 2 | 1 |  | 0
1.4.3 | Investigate outliers | ... | 2022-09-29 | 1 |  | 100% | 2022-09-29 | 2022-09-30 | 1 | 2 | 1 |  | 0
1.4.4 | Investigate underlying distribution of data/features | ... | 2022-09-29 | 1 |  | 100% | 2022-09-29 | 2022-09-30 | 1 | 2 | 1 |  | 0
1.4.4.1 | Take note of any skewness | ... | ... | ... |  | 100% | ... | ... | ... | #VALUE! | ... |  | ...
1.4.5 | Assess and treat missing values appropriately | ... | 2022-09-29 | 1 |  | 100% | 2022-09-29 | 2022-09-30 | 1 | 2 | 1 |  | 0
1.4.6 | Data validation step (e.g., Does data make sense?) | ... | 2022-09-29 | 1 |  | 100% | 2022-09-29 | 2022-09-30 | 1 | 2 | 1 |  | 0
1.5 | Generate new cases by randomly sampling each feature | ... | 2022-09-29 | 1 |  | 100% | 2022-09-29 | 2022-09-30 | 1 | 2 | 1 | 0 | 0 | 0
2 | Front-End | Rahil, Aaron | 2022-10-03 | 10 | #VALUE! | 22.58% | 2022-10-12 | - | 8 | #VALUE! | 2 | #VALUE! | 8 | #VALUE!
2.1 | Develop html/css/js home page | Rahil, Aaron | 2022-10-03 | 10 |  | 0% | 2022-10-12 | - | 8 | #VALUE! | 0 | 0 | 10 | 0
2.1.1 | (Proof of Concept) Write "hello world" on web page | Rahil | 2022-10-03 | 2 |  | 100% | 2022-10-04 | 2022-10-03 | 2 | 1 | 2 | 0 | 0 | 0
2.1.2 | Create "Welcome" message and "New User", "View Teams", and "Team Stats" buttons | Aaron | 2022-10-05 | 1 |  | 100% | 2022-10-05 | 2022-10-03 | 1 | -3 | 1 | 0 | 0 | 0
2.1.3 | Create html survey / "New User" page | Rahil, Aaron | 2022-10-05 | 4 |  | 100% | 2022-10-08 | 2022-10-08 | 3 | 3 | 4 | 0 | 0 | 0
2.1.3.1 | Develop "Submit" button functionality | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... | 0 | ... | 0
2.1.3.1.1 | Once Submit Button API is created, connect survey to API to send data to database on button click | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.3.1.2 | Once Submit Button API is created, redirect user back to home page on button click | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.4 | Create "View Teams" page | Rahil | 2022-10-05 | 4 |  | 0% | 2022-10-08 | - | 3 | #VALUE! | 0 |  | 4
2.1.4.1 | Once Team Lookup API is created, create search box to search database by individual user name | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.4.2 | On team selection, redirect user to new page that outputs team id/name and team members | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.4 | Create "Team Stats" page | Aaron | 2022-10-05 | 4 |  | 0% | 2022-10-08 | - | 3 | #VALUE! | 0 |  | 4
2.1.4.1 | Once Team Stats API is created, create search box to search database by team id/name | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.4.2 | On team selection, redirect user to new page that outputs attributes from Team database | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.5 | Develop "New User" button | Rahil, Aaron | 2022-10-10 | 2 |  | 0% | 2022-10-11 | - | 2 | #VALUE! | 0 |  | 2
2.1.5.1 | Embed hyperlink to "New User" survey/page | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.6 | Develop "View Teams" buttons | Rahil | 2022-10-10 | 2 |  | 0% | 2022-10-11 | - | 2 | #VALUE! | 0 |  | 2
2.1.6.1 | Embed hyperlink to "View Teams" page | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.7 | Develop "Team Stats" page | Aaron | 2022-10-10 | 2 |  | 0% | 2022-10-11 | - | 2 | #VALUE! | 0 |  | 2
2.1.7.1 | Embed hyperlink to "Team Stats" page | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
3 | Back-End and Middleware | Rahil | 2022-09-28 | 25 | #VALUE! | 37.22% | 2022-10-22 | - | 18 | #VALUE! | 9 | #VALUE! | 16 | #VALUE!
3.1 | Develop database schema | ... | 2022-09-28 | 2 |  | 100% | 2022-09-29 | 2022-10-01 | 2 | 3 | 2 | 0 | 0 | 0
3.2 | Create database in XAMPP / MySQL | ... | 2022-09-30 | 3 |  | 100% | 2022-10-02 | 2022-10-03 | 1 | 2 | 3 | 0 | 0 | 0
3.3 | Create database tables in XAMPP / MySQL | ... | 2022-09-30 | 3 |  | 100% | 2022-10-02 | 2022-10-03 | 1 | 2 | 3 | 0 | 0 | 0
3.4 | Create Team Stats API | ... | 2022-10-15 | 5 |  | 0% | 2022-10-19 | 2022-10-14 | 3 | -1 | 0 | 0 | 5 | 0
3.4.1 | API receives team ID and outputs filtered Team Stats table | ... | ... | ... |  | ... | ... | ... | ... | ... | ... |  | ...
3.5 | Create Team Lookup / View Results API | ... | 2022-10-15 | 5 |  | 0% | 2022-10-19 | 2022-10-14 | 3 | -1 | 0 |  | 5
3.5.1 | converts database users into JSON objects | ... | ... | ... |  | ... | ... | ... | ... | ... | ... |  | ...
3.6 | Create New User API (API takes survey input and outputs into master table in team-builder DB) | ... | 2022-10-05 | 18 |  | 30% | 2022-10-22 | 2022-10-14 | 13 | 8 | 5 |  | 13
4 | Create team-builder | Rahil | 2022-10-05 | 15 | #VALUE! | 40% | 2022-10-19 | - | 11 | #VALUE! | 6 | #VALUE! | 9 | #VALUE!
4.1 | Develop similarity/dissimilarity-based clustering model in Azure ML Designer | ... | 2022-10-05 | 15 |  | 40% | 2022-10-19 | - | 11 | #VALUE! | 6 | 0 | 9 | 0
5 | Application Hosting | Aaron Yang | 2022-09-28 | 24 | #VALUE! | 61.11% | 2022-10-21 | - | 18 | #VALUE! | 14 | #VALUE! | 10 | #VALUE!
5.1 | Create local XAMPP Server (main development done offline) - DONE INDIVIDUALLY | ... | 2022-10-01 | 2 |  | 100% | 2022-10-02 | - | 0 | #VALUE! | 2
5.2 | Create web server through Azure | ... | 2022-10-07 | 7 |  | 100% | 2022-10-13 | 2022-10-08 | 5 | 1 | 7 | 0 | 0 | 0
5.3 | Manage API access in Azure | ... | 2022-10-15 | 7 |  | 0% | 2022-10-21 | - | 5 | #VALUE! | 0 | 0 | 7 | 0
5.3 | Push master git branch into Azure server | ... | 2022-10-13 | 2 |  | 100% | 2022-10-14 | 2022-10-08 | 2 | -4 | 2 | 0 | 0 | 0
6 | Class Deliverables | All | 2022-09-18 | 85 | 87 | 35% | 2022-12-11 | 2022-12-13 | 60 | 62 | 29 | 30 | 56 | 57
6.1 | Charts and Networks | ... | 2022-09-18 | 6 |  | 100% | 2022-09-23 | 2022-09-25 | -1 | 5 | 6 | 0 | 0 | 0
6.2 | Midterm Presentation | All | 2022-09-28 | 5 |  | 100% | 2022-10-02 | 2022-10-02 | 0 | 3 | 5 | 0 | 0 | 0
6.3 | Midterm: Peer Reviews and Grading | All | 2022-10-07 | 2 |  | 100% | 2022-10-08 | 2022-10-11 | -2 | 3 | 2 | 0 | 0 | 0
6.4 | Response to Reviews Comments (Midterm) | All | 2022-10-11 | 1 |  | 100% | 2022-10-11 | 2022-10-11 | 1 | 1 | 1 | 0 | 0 | 0
6.5 | Midterm: Individual Submissions | All | 2022-10-10 | 3 |  | 100% | 2022-10-12 | 2022-10-11 | 2 | 2 | 3 | 0 | 0 | 0
6.6 | Online Mandatory Feedback Session 2 | All | 2022-10-13 | 1 |  | 100% | 2022-10-13 | 2022-10-13 | 1 | 1 | 1 | 0 | 0 | 0
6.7 | Implementation | ... | 2022-10-14 | 5 |  | 100% | 2022-10-18 | 2022-10-16 | 2 | 1 | 5 | 0 | 0 | 0
6.8 | In-Person Feedback Session 3 | ... | 2022-10-13 | 1 |  | 10% | 2022-10-13 | 2022-10-18 | -4 | 4 | 0 | 0 | 1 | 0
6.9 | In-Person Feedback Session 4 | ... | 2022-10-20 | 1 |  | 0% | 2022-10-20 | 2022-10-20 | 1 | 1 | 0 | 0 | 1 | 0
6.10 | Enhanced Implementation | ... | 2022-10-21 | 8 |  | 0% | 2022-10-28 | 2022-10-30 | -1 | 6 | 0 | 0 | 8 | 0
6.11 | Online Mandatory Feedback Session 3 | ... | 2022-11-03 | 1 |  | 0% | 2022-11-03 | 2022-11-03 | 1 | 1 | 0 | 0 | 1 | 0
6.12 | Testing | ... | 2022-11-01 | 5 |  | 0% | 2022-11-05 | 2022-11-06 | 0 | 4 | 0 | 0 | 5 | 0
6.13 | Revise, Redo | ... | 2022-11-07 | 6 |  | 0% | 2022-11-12 | 2022-11-13 | 0 | 5 | 0 | 0 | 6 | 0
6.14 | Results, Conclusions, Future Work | ... | 2022-11-14 | 5 |  | 0% | 2022-11-18 | 2022-11-18 | 1 | 5 | 0 | 0 | 5 | 0
6.15 | Exit Survey | ... | 2022-11-18 | 2 |  | 0% | 2022-11-19 | 2022-11-20 | 0 | 1 | 0 | 0 | 2 | 0
6.16 | Online Mandatory Feedback Session 4 | ... | 2022-11-24 | 1 |  | 0% | 2022-11-24 | 2022-11-24 | 1 | 1 | 0 | 0 | 1 | 0
6.17 | Written Report + PPT + Presentation | ... | 2022-11-20 | 7 |  | 0% | 2022-11-26 | 2022-11-27 | 0 | 5 | 0 | 0 | 7 | 0
6.18 | In-Person Feedback Session 5 | ... | 2022-11-29 | 1 |  | 0% | 2022-11-29 | 2022-11-29 | 1 | 1 | 0 | 0 | 1 | 0
6.19 | In-Person Feedback Session 6 | ... | 2022-11-29 | 1 |  | 0% | 2022-11-29 | 2022-12-01 | -3 | 3 | 0 | 0 | 1 | 0
6.20 | Return of Peer Reviews (Team) | ... | 2022-12-08 | 1 |  | 0% | 2022-12-08 | 2022-12-09 | -2 | 2 | 0 | 0 | 1 | 0
6.21 | Return of Peer Reviews (Individual Assessment) | ... | 2022-12-08 | 1 |  | 0% | 2022-12-08 | 2022-12-09 | -2 | 2 | 0 | 0 | 1 | 0
6.22 | Reponse to Reviewers' Comments | ... | 2022-12-10 | 2 |  | 0% | 2022-12-11 | 2022-12-13 | -2 | 2 | 0 | 0 | 2 | 0
TEMPLATE ROWS (do not modify)
1 | Project 1 |  | 2014-12-31 | 15 | 15 | 68.8% | 2015-01-14 | 2015-01-14 | 11 | 11 | 10 | 10 | 5 | 5
1.1 | Sub Project (Level 1) |  | 2015-01-01 | 14 |  | 80% | 2015-01-14 | 2015-01-14 | 10 | 10 | 11 | 0 | 3 | 0
1.1.1 | Sub Project (Level 2) |  | 2014-12-31 | 5 |  | 60% | 2015-01-04 | 2015-01-04 | 3 | 3 | 3 | 0 | 2 | 0
1.1.1.1 | Sub Project (Level 3) |  | 2015-01-01 | 2 |  | 50% | 2015-01-02 | 2015-01-02 | 2 | 2 | 1 | 0 | 1 | 0
1.1.1.1.1 | Sub Project (Level 4) |  | 2015-01-01 | 4 |  | 50% | 2015-01-04 | 2015-01-04 | 2 | 2 | 2 | 0 | 2 | 0

## Dependency Chart
Team-Builder
| Today's Date | 2022-11-06 | [12 empty] | © 2022 Spreadsheet123 LTD
| Project Manager | Aaron Yang
| Week Starts from | Monday
| Start Date | 2022-09-18
0
[16 empty] | Sep 2022 | [11 empty] | Oct 2022 | [30 empty] | Nov 2022 | [29 empty] | Dec 2022 | [30 empty] | Jan 2023
WBS | Tasks Name | Assigned to: | Date | Duration | Act. Duration | Complete | Projected End | Actual End | Assigned | Act. Assigned | Complete | Act. Complete | Remaining | Act. Remaining | time axis 2022-09-19 to 2023-01-16
1 | Data Collection | All | 2022-09-19 |  | 13 | 27.25% | 2022-10-01 | 2022-10-01 | 10 | 10 | 0 | 3 | 0 | 10
1.1 | Create survey questions | All | 2022-09-19 | 3 |  | 100% | 2022-09-21 | 2022-09-21 | 3 | 3 | 3 | 0 | 0 | 0
1.2 | Deploy survey | All | 2022-09-22 | 7 |  | 35% | 2022-09-28 | - | 5 | #VALUE! | 2 | 0 | 5 | 0
1.3 | Create github repo | All | 2022-09-28 | 1 |  | 0% | 2022-09-28 | - | 1 | #VALUE! | 0 |  | 1
1.4 | Clean and explore data | All | 2022-09-29 | 2 |  | 0% | 2022-09-30 | - | 2 | #VALUE! | 0 | 0 | 2 | 0
1.4.1 | Assess and remove any duplicate observations | Rahil | 2022-09-29 | 1 |  | 0% | 2022-09-29 | - | 1 | #VALUE! | 0 |  | 1
1.4.2 | Investigate and fix any structural errors (e.g., typos, data inconsistencies, etc.) | Aaron | 2022-09-29 | 1 |  | 0% | 2022-09-29 | - | 1 | #VALUE! | 0 |  | 1
1.4.3 | Investigate outliers | Rahil | 2022-09-29 | 1 |  | 0% | 2022-09-29 | - | 1 | #VALUE! | 0 |  | 1
1.4.4 | Investigate underlying distribution of data/features | Taylor | 2022-09-30 | 1 |  | 0% | 2022-09-30 | - | 1 | #VALUE! | 0 |  | 1
1.4.4.1 | Take note of any skewness | ... | ... | ... |  | 0% | ... | ... | ... | #VALUE! | ... |  | ...
1.4.5 | Assess and treat missing values appropriately | Aaron | 2022-09-29 | 1 |  | 0% | 2022-09-29 | - | 1 | #VALUE! | 0 |  | 1
1.4.6 | Data validation step (e.g., Does data make sense?) | Aaron | 2022-09-29 | 1 |  | 0% | 2022-09-29 | - | 1 | #VALUE! | 0 |  | 1
1.5 | Augment data using SMOTE | Taylor | 2022-10-01 | 1 |  | 0% | 2022-10-01 | - | 0 | #VALUE! | 0 | 0 | 1 | 0
2 | Front-End | Rahil, Aaron | 2022-10-03 | 10 | #VALUE! | 0% | 2022-10-12 | - | 8 | #VALUE! | 0 | #VALUE! | 10 | #VALUE!
2.1 | Develop html/css/js home page | Rahil, Aaron | 2022-10-03 | 10 |  | 0% | 2022-10-12 | - | 8 | #VALUE! | 0 | 0 | 10 | 0
2.1.1 | (Proof of Concept) Write "hello world" on web page | Rahil | 2022-10-03 | 2 |  | 0% | 2022-10-04 | - | 2 | #VALUE! | 0 | 0 | 2 | 0
2.1.2 | Create "Welcome" message and "New User", "View Teams", and "Team Stats" buttons | Aaron | 2022-10-05 | 1 |  | 0% | 2022-10-05 | - | 1 | #VALUE! | 0 | 0 | 1 | 0
2.1.3 | Create html survey / "New User" page | Rahil, Aaron | 2022-10-05 | 4 |  | 0% | 2022-10-08 | - | 3 | #VALUE! | 0 | 0 | 4 | 0
2.1.3.1 | Develop "Submit" button functionality | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... | 0 | ... | 0
2.1.3.1.1 | Once Submit Button API is created, connect survey to API to send data to database on button click | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.3.1.2 | Once Submit Button API is created, redirect user back to home page on button click | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.4 | Create "View Teams" page | Rahil | 2022-10-05 | 4 |  | 0% | 2022-10-08 | - | 3 | #VALUE! | 0 |  | 4
2.1.4.1 | Once Team Lookup API is created, create search box to search database by individual user name | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.4.2 | On team selection, redirect user to new page that outputs team id/name and team members | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.5 | Create "Team Stats" page | Aaron | 2022-10-05 | 4 |  | 0% | 2022-10-08 | - | 3 | #VALUE! | 0 |  | 4
2.1.5.1 | Once Team Stats API is created, create search box to search database by team id/name | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.5.2 | On team selection, redirect user to new page that outputs attributes from Team database | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.6 | Develop "New User" button | Rahil, Aaron | 2022-10-10 | 2 |  | 0% | 2022-10-11 | - | 2 | #VALUE! | 0 |  | 2
2.1.6.1 | Embed hyperlink to "New User" survey | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.7 | Develop "View Teams" buttons | Rahil | 2022-10-10 | 2 |  | 0% | 2022-10-11 | - | 2 | #VALUE! | 0 |  | 2
2.1.7.1 | Embed hyperlink to "View Teams" page | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
2.1.8 | Develop "Team Stats" page | Aaron | 2022-10-10 | 2 |  | 0% | 2022-10-11 | - | 2 | #VALUE! | 0 |  | 2
2.1.8.1 | Embed hyperlink to "Team Stats" page | ... | ... | ... |  | 0% | ... | ... | ... | ... | ... |  | ...
3 | Back-End and Middleware | Taylor | 2022-09-27 | 4 | #VALUE! | 0% | 2022-09-30 | - | 4 | #VALUE! | 0 | #VALUE! | 4 | #VALUE!
3.1 | Develop database schema | ... | 2022-09-27 | 2 |  | 0% | 2022-09-28 | - | 2 | #VALUE! | 0 | 0 | 2 | 0
3.2 | Create main user database in SQL Server | ... | 2022-09-28 | 2 |  | 0% | 2022-09-29 | - | 2 | #VALUE! | 0 | 0 | 2 | 0
3.3 | Create team database in SQL Server | ... | 2022-09-28 | 2 |  | 0% | 2022-09-29 | - | 2 | #VALUE! | 0 | 0 | 2 | 0
3.4 | Create Team Stats API | ... | 2022-09-30 | 1 |  | 0% | 2022-09-30 | - | 1 | #VALUE! | 0 | 0 | 1 | 0
3.4.1 | API recieves team input and outputs filtered Team Stats table | ... | ... | ... |  | ... | ... | ... | ... | ... | ... |  | ...
3.5 | Create Team Lookup API | ... | 2022-09-30 | 1 |  | 0% | 2022-09-30 | - | 1 | #VALUE! | 0 |  | 1
3.5.1 | API converts database users into JSON objects | ... | ... | ... |  | ... | ... | ... | ... | ... | ... |  | ...
3.6 | Create Submit Button API | ... | 2022-09-30 | 1 |  | 0% | 2022-09-30 | - | 1 | #VALUE! | 0 |  | 1
4 | Create team-builder | All | 2022-10-05 | 7 | #VALUE! | 0% | 2022-10-11 | - | 5 | #VALUE! | 0 | #VALUE! | 7 | #VALUE!
4.1 | Develop similarity/dissimilarity-based clustering model in Azure ML Designer | ... | 2022-10-05 | 7 |  | 0% | 2022-10-11 | - | 5 | #VALUE! | 0 | 0 | 7 | 0
5 | Application Hosting | Taylor | 2022-09-28 | 16 | #VALUE! | 0% | 2022-10-13 | - | 12 | #VALUE! | 0 | #VALUE! | 16 | #VALUE!
5.1 | Create web server through Azure (main development done in local server thru XAMPP) | ... | 2022-09-28 | 7 |  | 0% | 2022-10-04 | - | 5 | #VALUE! | 0 | 0 | 7 | 0
5.2 | Manage API access in Azure | ... | 2022-09-28 | 7 |  | 0% | 2022-10-04 | - | 5 | #VALUE! | 0 | 0 | 7 | 0
5.3 | Push master git branch into Azure server | ... | 2022-10-12 | 2 |  | 0% | 2022-10-13 | - | 2 | #VALUE! | 0 | 0 | 2 | 0
6 | Class Deliverables | All | 2022-09-18 | 85 | 87 | 9.091% | 2022-12-11 | 2022-12-13 | 60 | 62 | 7 | 7 | 78 | 80
6.1 | Charts and Networks | ... | 2022-09-18 | 6 |  | 100% | 2022-09-23 | 2022-09-25 | -1 | 5 | 6 | 0 | 0 | 0
6.2 | Midterm Presentation | ... | 2022-09-28 | 5 |  | 0% | 2022-10-02 | 2022-10-02 | 0 | 3 | 0 | 0 | 5 | 0
6.3 | Midterm: Peer Reviews and Grading | ... | 2022-10-07 | 2 |  | 0% | 2022-10-08 | 2022-10-09 | 0 | 1 | 0 | 0 | 2 | 0
6.4 | Response to Reviews Comments (Midterm) | ... | 2022-10-11 | 1 |  | 0% | 2022-10-11 | 2022-10-11 | 1 | 1 | 0 | 0 | 1 | 0
6.5 | Midterm: Individual Submissions | ... | 2022-10-08 | 3 |  | 0% | 2022-10-10 | 2022-10-11 | -2 | 2 | 0 | 0 | 3 | 0
6.6 | Online Mandatory Feedback Session 2 | ... | 2022-10-13 | 1 |  | 0% | 2022-10-13 | 2022-10-13 | 1 | 1 | 0 | 0 | 1 | 0
6.7 | Implementation | ... | 2022-10-11 | 5 |  | 0% | 2022-10-15 | 2022-10-16 | 0 | 4 | 0 | 0 | 5 | 0
6.8 | In-Person Feedback Session 3 | ... | 2022-10-18 | 1 |  | 0% | 2022-10-18 | 2022-10-18 | 1 | 1 | 0 | 0 | 1 | 0
6.9 | In-Person Feedback Session 4 | ... | 2022-10-20 | 1 |  | 0% | 2022-10-20 | 2022-10-20 | 1 | 1 | 0 | 0 | 1 | 0
6.10 | Enhanced Implementation | ... | 2022-10-21 | 8 |  | 0% | 2022-10-28 | 2022-10-30 | -1 | 6 | 0 | 0 | 8 | 0
6.11 | Online Mandatory Feedback Session 3 | ... | 2022-11-03 | 1 |  | 0% | 2022-11-03 | 2022-11-03 | 1 | 1 | 0 | 0 | 1 | 0
6.12 | Testing | ... | 2022-11-01 | 5 |  | 0% | 2022-11-05 | 2022-11-06 | 0 | 4 | 0 | 0 | 5 | 0
6.13 | Revise, Redo | ... | 2022-11-07 | 6 |  | 0% | 2022-11-12 | 2022-11-13 | 0 | 5 | 0 | 0 | 6 | 0
6.14 | Results, Conclusions, Future Work | ... | 2022-11-14 | 5 |  | 0% | 2022-11-18 | 2022-11-18 | 1 | 5 | 0 | 0 | 5 | 0
6.15 | Exit Survey | ... | 2022-11-18 | 2 |  | 0% | 2022-11-19 | 2022-11-20 | 0 | 1 | 0 | 0 | 2 | 0
6.16 | Online Mandatory Feedback Session 4 | ... | 2022-11-24 | 1 |  | 0% | 2022-11-24 | 2022-11-24 | 1 | 1 | 0 | 0 | 1 | 0
6.17 | Written Report + PPT + Presentation | ... | 2022-11-20 | 7 |  | 0% | 2022-11-26 | 2022-11-27 | 0 | 5 | 0 | 0 | 7 | 0
6.18 | In-Person Feedback Session 5 | ... | 2022-11-29 | 1 |  | 0% | 2022-11-29 | 2022-11-29 | 1 | 1 | 0 | 0 | 1 | 0
6.19 | In-Person Feedback Session 6 | ... | 2022-11-29 | 1 |  | 0% | 2022-11-29 | 2022-12-01 | -3 | 3 | 0 | 0 | 1 | 0
6.20 | Return of Peer Reviews (Team) | ... | 2022-12-08 | 1 |  | 0% | 2022-12-08 | 2022-12-09 | -2 | 2 | 0 | 0 | 1 | 0
6.21 | Return of Peer Reviews (Individual Assessment) | ... | 2022-12-08 | 1 |  | 0% | 2022-12-08 | 2022-12-09 | -2 | 2 | 0 | 0 | 1 | 0
6.22 | Reponse to Reviewers' Comments | ... | 2022-12-10 | 2 |  | 0% | 2022-12-11 | 2022-12-13 | -2 | 2 | 0 | 0 | 2 | 0

## HELP (hidden)
HELP
Terminology
| WBS | Work Breakdown Structure
| Predecessor | Task that has been followed or replaced by another
Help
How to begin using Gantt Chart?
● Only modify cells with Blue background, including Week Starts from and Start Date, which determines
the first day of the gantt chart.
● Cells with Grey background in column Task Name and Assigned To can also be modified as well as other
cells, but with care as they contain formulas, which summarize information from all subtasks of that
project.
● You can begin gantt chart from any day of the week by choosing it from the drop down list in cell C8.
● Only 120 days are shown at once, the Gantt Chart is limited by maximum 365 days, but you can adjust it
by changing settings of the scrollbar.
● Use the scrollbar to change the range of dates displayed on the gantt chart.
How can I print the Gantt Chart?
To print the Gantt Chart first you need to define the printing area by selecting the range of cells that you
want to print then go to Page Layout tab in the ribbon, click on the Print Area > Set Print Area.
Important: The number of selected cells can be wider than default printing area which may results in
split printouts.
To adjust print out scaling or orientation click on Margins > Custom Margins then in the dialogue window
click on the Page tab and adjust printing Orientation and Scaling settings as desired.
How to start task after the end of predecessor task?
When you need to start new task after the end of predecessor task, you can do the following:
in the Start Date you can enter the following formula =ActualEnd + 1 or =WORKDAY(ActualEnd,1) to start
new task on the next working day, where ActualEnd is the date of the end of predecessor task in the
column Actual End.
What is the difference between Duration and Actual Duration?
The Duration is used to define expected duration of the task. Actual Duration defines the total length of
time of the task - even if it exceeds the predicted duration or if the task was finished ahead of schedule.
For your convenience, Actual Duration corrects Actual End date and thereby adjusts start date of any
following tasks when you use formula to enter start date as explained above.
How to insert new tasks and subtasks in to the project?
The Project Manager Gantt Chart contains Template rows, which you can use to insert new tasks into your
project. You can copy entire row by clicking on the row reference number then copy it (Ctrl + C) then right
click on the row reference above which you need to insert your new task and select Insert Copied Cell.
Note that WBS task and subtask numbering is automated. You can also use the same technique to insert
new projects.
If you are inserting new task after the last task be sure to check formulas in following columns:
Date, Complete, Projected End and Actual End. Each of this formulas contain references to the cells
below =MAX(H41:H46) or =SUMPRODUCT(E41:E46,G41:G46)/SUM(E41:E46) where the range H41:H46,
E41:E46 and G41:G46 is the range of cells that this formula computes. You can change this references to
include new tasks.
Click to veiw video help
Need more help or have a question?
| For any questions regarding use of this template please email us. |  | Send e-mail

## Project Gantt Chart Pro (hidden)
PROJECT GANTT CHART PRO
Benefits of Project Manager Gantt Chart Pro
Project Manager Gantt Chart Pro is completely Unlocked, which is giving you the ability
for further customisation.
Ability to create task dependencies with use of predecessor.
More ways to define task duration.
Gantt Chart Daily, Weekly and Monthly views, great for projects with long durations.
Ability to Include/Exclude Weekends
Ability to Include/Exclude Holidays which can be defined on the Settings Tab.
Lifetime Updates and Upgrades.

## ©
Terms of Use - EULA
© 2022 Spreadsheet123 LTD. All rights reserved
IMPORTANT—READ CAREFULLY:
This End-User License Agreement (”EULA”) is a legal agreement between you and Spreadsheet123.com that
covers all Microsoft Excel and OpenOffice.org templates or spreadsheets (”TEMPLATES”) and software ("SOFTWARE") made
by Spreadsheet123.com.
By downloading, copying, accessing or otherwise using any TEMPLATES or/and SOFTWARE, you agree to be bound by the
terms of this EULA.
TEMPLATES LICENSE
This TEMPLATE is protected by copyright laws and international copyright treaties, as well as other intellectual
property laws and treaties. Each TEMPLATE is licensed, not sold.
1. GRANT OF LICENSE.
This EULA grants you the right to download this TEMPLATE free of charge for personal use or use within your company
or organization.
You may customize this TEMPLATE with you personal information and use for its intended purpose in personal calculations
documentation or/and communications, but you may not remove or alter any logo, trademark, copyright, hyperlinks,
disclaimers, terms of use or other proprietary notices within this TEMPLATE.
You may not sell, resell, license, rent, lease, lend or otherwise transfer for value without written
permission of SPREADSHEET123.COM
You may not distribute this TEMPLATE in any stand-alone products that contain only the TEMPLATE, or as part of any other
product. You may not copy or post any TEMPLATE on any network computer or broadcast it in any media without
written permission of SPREADSHEET123.COM.
2. RESERVATION OF RIGHTS.
All title and copyrights in and to the Template, and any copies of the Template, are owned by Spreadsheet123.com.
All rights not expressly granted are reserved by Spreadsheet123.com. In particular, this EULA does not grant you any
rights in connection with any trademarks or service marks of Spreadsheet123.com. Use of any Template for any purpose
other than expressly permitted in this EULA is prohibited, and may result in severe civil and criminal penalties.
3. TERMINATION.
Without prejudice to any other rights, Spreadsheet123.com may terminate this EULA if you fail to comply with the
terms and conditions of this EULA. In such event, you must destroy all copies of any TEMPLATE.
4. NOTICE SPECIFIC TO TEMPLATES.
SPREADSHEET123.COM MAKE NO REPRESENTATIONS
ABOUT THE SUITABILITY OF THE TEMPLATES FOR ANY PURPOSE. ALL TEMPLATES ARE PROVIDED
“AS IS” WITHOUT WARRANTY OF ANY KIND. SPREADSHEET123.COM HEREBY DISCLAIM ALL
WARRANTIES AND CONDITIONS WITH REGARD TO THE TEMPLATES, INCLUDING ALL IMPLIED
WARRANTIES AND CONDITIONS OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, TITLE
AND NON-INFRINGEMENT. IN NO EVENT SHALL SPREADSHEET123.COM BE LIABLE FOR ANY SPECIAL,
INDIRECT OR CONSEQUENTIAL DAMAGES OR ANY DAMAGES WHATSOEVER RESULTING FROM LOSS
OF USE, DATA OR PROFITS, WHETHER IN AN ACTION OF CONTRACT, NEGLIGENCE OR OTHER TORTIOUS
ANY REFERENCES TO EVENTS, PEOPLE, PLACES, OR ENTITIES IN THE TEMPLATES IS PURELY FICTITIOUS AND NOT INTENDED TO REPRESENT ANY ACTUAL EVENT,
PERSON, PLACE, OR ENTITY. SPREADSHEET123.COM DISCLAIMS ANY LIKENESS OR SIMILARITIES TO ACTUAL EVENTS, PEOPLE, PLACES, OR ENTITIES, AND
ANY SUCH LIKENESS OR SIMILARITIES ARE UNINTENTIONAL AND PURELY COINCIDENTAL.
5. MISCELLANEOUS.
Some states do not allow the limitation or exclusion of liability for incidental or consequential
damages, so the above limitation may not apply to you.